## Marco Lógico
Marco Lógico
Nombre del proyecto | ConEsperanza
Fecha inicio | 2026-05-15 | Fecha fin |  |  |  | 2026-11-15
Responsable | CARE | Socio |  |  |  | NA
Total participantes directos | 28632 (23.251 ÚNICOS)
Territorios | Cauca (Buenos Aires y Morales) , Norte de Santander (Ocaña, Abrego, Harací, Teorama, La Playa de Belén, Convención)
Presupuesto | 2261471 USD
Objetivo General | Indicadores | Metas |  | Responsable | Notas | Medios de verificación
Respuesta de emergencia para salvar vidas dirigida a comunidades que se enfrentan graves necesidades humanitarias en municipios prioritarios de Colombia. | % de participantes que afirman que la ayuda humanitaria se presta de manera segura, accesible, responsable y participativa | 80% |  | CARE |  | Encuestas de Satisfacción y PDM
Actividades /productos | Indicadores | Metas doble conteo | Metas únicos | Responsable | Notas | Medios de verificación
1. Protección
1.1 Sensibilización comunitaria, difusión de información y campañas de comunicación sobre los mecanismos de protección disponibles para la población destinataria, para la prevención de riesgos de protección, la violanción de los derechos y la prevención de la violencia basada en género. Actividad estándar OCHA: C-CA19. ACTIVITY. Establishment of protection and prevention mechanisms by identifying high-risk areas and risk factors driving violence against women and girls in the emergency. Strengthen or set up prevention and mitigation strategies, mechanisms and initiatives in support of national and community-based interventions in line with IASC principles and guidelines. Risk mitigation strategies may include the provision of dignity kits and other means of sharing life-saving protection information. | C-CA19. INDICATOR 74: Number of individuals who received life‑saving protection support through newly established or strengthened violence prevention and risk‑mitigation mechanisms. | 8000 | 8000 | CARE |  | 1. Listados de Asistencia 2. Actas de actividad (espacios masivos) 3. Registro en CommCare 4. BBDD sistema de monitoreo CARE COL 5. Archivo seguimiento eventos masivos
1.2 Gestión de casos para personas víctimas de conflicto armado, en situación de riesgo o sobrevivientes de violencia de género, incluyendo derivaciones internas y externas Actividad estándar OCHA: C-CA11. ACTIVITY: Provision of life-saving support to people with specific needs, survivors of violence against women and girls and/or sexual exploitation and abuse. This includes strengthening psychosocial support (PSS) programming and non- specialized Mental Health and Psychosocial Support Services (MHPSS) to individuals, families, and communities that have been exposed to conflict and displacement, political oppression, torture, and violence against women and girls; and support in promoting community mobilization, activating social networks, and the establishment of community centers and safe spaces. | C-CA11. INDICATOR 65. Number of people receiving violence psycho-social support and/or violence case management | 1152 | 0 | CARE |  | 1. Registro de todo el ciclo de la Gestión de Caso en el sistema de monitoreo de CARE COL 2. BBDD sistema de monitoreo CARE COL
1.3 Entrega de cash a personas en situación de riesgo o sobrevivientes de violencia de género priorizadas en el proceso de gestión de casos Actividad estándar OCHA: C-CA16. ACTIVITY. Provision of financial, cash or voucher / CVA assistance for protection outcomes | C-CA16. INDICATOR. Number of people affected benefiting from emergency cash assistance or direct service payments | 403 | 0 | CARE |  | 1. Registro entrega de priorización y entrega de cash en el sistema de monitoreo 2. Tirillas de entrega del cash - proveedor de servicios financieros (ventanilla) /BBDD proveedor 3. BBDD sistema de monitoreo CARE COL 4. BBDD seguimiento coordinación PTM
1.4 Entrega de kits - CARE Package- Actividad estándar OCHA: C-CA19. ACTIVITY. Establishment of protection and prevention mechanisms by identifying high-risk areas and risk factors driving violence against women and girls in the emergency. Strengthen or set up prevention and mitigation strategies, mechanisms and initiatives in support of national and community-based interventions in line with IASC principles and guidelines. Risk mitigation strategies may include the provision of dignity kits and other means of sharing life-saving protection information. | C-CA19. INDICATOR 74: Number of individuals who received life‑saving protection support through newly established or strengthened violence prevention and risk‑mitigation mechanisms. | 9600 | 7200 | CARE | *Son 2400 kits entregados a hogares (x 4 miembros) | 1. Registro entrega de kits en el sistema de monitoreo 2. Listados de distribución de kits 2. BBDD sistema de monitoreo CARE COL
1.5 Fortalecimiento protección en espacios seguros, gestionados por organizaciones de base, institucionalidad del gobierno y organismos homólogos. Actividad estándar OCHA: C-CA11. ACTIVITY: Provision of life-saving support to people with specific needs, survivors of violence against women and girls and/or sexual exploitation and abuse. This includes strengthening psychosocial support (PSS) programming and non- specialized Mental Health and Psychosocial Support Services (MHPSS) to individuals, families, and communities that have been exposed to conflict and displacement, political oppression, torture, and violence against women and girls; and support in promoting community mobilization, activating social networks, and the establishment of community centers and safe spaces. | C-CA11. INDICATOR 65. Number of people receiving violence psycho-social support and/or violence case management | 5400 | 5400 | CARE |  | 1. Mapeo y diagnóstico 2. Plan de trabajo 3. Acta de entrega (dotación - mejoras) 4. Actas de seguimiento 5. Archivo consolidado de seguimiento
2. Salud
2.1 Prestación de servicios de atención primaria de salud Actividad estándar OCHA: C-CA1: ACTIVITY. Ensuring equitable and timely access to emergency primary healthcare, including the link with community health systems and outreach activities. | C-CA1. INDICATOR 28: Number of primary healthcare consultations provided | 1345 | 1211 | CARE | *2.690 consultas (en promedio dos por persona) | 1. Voucher de salud en el sistema de monitoreo 2. BBDD sistema de monitoreo CARE COL 3. BBDD proveedor de servicios
2.2 Entre kits postparto Actividad estándar OCHA: C-CA1: ACTIVITY. Ensuring equitable and timely access to emergency primary healthcare, including the link with community health systems and outreach activities. | C-CA1. INDICATOR 28: Number of primary healthcare consultations provided | 140 | 0 | CARE |  | 1. Registro entrega de kits en el sistema de monitoreo 2. Listados de distribución de kits 2. BBDD sistema de monitoreo CARE COL
2.3 Prestación de servicios de atención medica a las personas sobrevientes de violencia sexual Actividad estándar OCHA: C-CA11: ACTIVITY. Medical (including psychological) support to survivors of sexual violence and other forms of violence against women and girls. This can include Mental Health and Psychosocial Support (MHPSS), refresher training for frontline health staff on clinical management of rape and intimate partner violence (IPV), and supply of drugs, material and equipment including through interagency reproductive health kits. | C-CA11. INDICATOR 43: Number of violence survivors receiving medical assistance, including clinical management of rape | 576 | 0 | CARE |  | 1. Voucher de salud en el sistema de monitoreo 2. BBDD sistema de monitoreo CARE COL 3. BBDD proveedor de servicios
3. Cash multipropósito
3.1 Cash Multipropósito Actividad estándar OCHA: C-CA1. ACTIVITY: Provision of multi purpose cash | C-CA1. INDICATOR 117: Number of households having received Multi-Purpose Cash (MPC) | 2016 | 1440 | CARE | *576 hogares (x 3.5 miembros) | 1. Registro en CommCare 2. BBDD entrega Cash 3. Tirillas entrega del proveedor de serivicio / BBDD proveedor 4. BBDD seguimiento coordinación PTM
Total participantes directos |  | 28632 | 23251

## Detalle metas
Sector | Actividad | Meta total | Cauca | Buenos Aires | May | Jun | Jul | Ago | Sep | Oct | Nov | Morales | May | Jun | Jul | Ago | Sep | Oct | Nov | Norte de Santander | Abrego | May | Jun | Jul | Ago | Sep | Oct | Nov | Ocaña | May | Jun | Jul | Ago | Sep | Oct | Nov | Convención | May | Jun | Jul | Ago | Sep | Oct | Nov | Teorama | May | Jun | Jul | Ago | Sep | Oct | Nov | Hacarí | May | Jun | Jul | Ago | Sep | Oct | Nov | La Playa de Belén | May | Jun | Jul | Ago | Sep | Oct | Nov
Protección | Sensibilizaciones general (10%) | 1600 | 480 | 240 | 0 | 24 | 54 | 54 | 54 | 54 | 0 | 240 | 0 | 24 | 54 | 54 | 54 | 54 | 0 | 1120 | 240 | 0 | 24 | 54 | 54 | 54 | 54 | 0 | 240 | 0 | 24 | 54 | 54 | 54 | 54 | 0 | 160 | 0 | 16 | 36 | 36 | 36 | 36 | 0 | 160 | 0 | 16 | 36 | 36 | 36 | 36 | 0 | 160 | 0 | 16 | 36 | 36 | 36 | 36 | 0 | 160 | 0 | 16 | 36 | 36 | 36 | 36 | 0
Protección | Sensibilizaciones VBG (80%) | 6400 | 1920 | 960 | 0 | 96 | 216 | 216 | 216 | 216 | 0 | 960 | 0 | 96 | 216 | 216 | 216 | 216 | 0 | 4480 | 960 | 0 | 96 | 216 | 216 | 216 | 216 | 0 | 960 | 0 | 96 | 216 | 216 | 216 | 216 | 0 | 640 | 0 | 64 | 144 | 144 | 144 | 144 | 0 | 640 | 0 | 64 | 144 | 144 | 144 | 144 | 0 | 640 | 0 | 64 | 144 | 144 | 144 | 144 | 0 | 640 | 0 | 64 | 144 | 144 | 144 | 144 | 0
Protección | Gestión de Casos | 1152 | 576 | 288 | 0 | 48 | 60 | 60 | 60 | 60 | 0 | 288 | 0 | 48 | 60 | 60 | 60 | 60 | 0 | 576 | 96 | 0 | 16 | 20 | 20 | 20 | 20 | 0 | 96 | 0 | 16 | 20 | 20 | 20 | 20 | 0 | 96 | 0 | 16 | 20 | 20 | 20 | 20 | 0 | 96 | 0 | 16 | 20 | 20 | 20 | 20 | 0 | 96 | 0 | 16 | 20 | 20 | 20 | 20 | 0 | 96 | 0 | 16 | 20 | 20 | 20 | 20 | 0
Protección | Cash VBG | 403 | 230 | 115 | 0 | 15 | 25 | 25 | 25 | 25 | 0 | 115 | 0 | 15 | 25 | 25 | 25 | 25 | 0 | 173 | 29 | 0 | 3 | 7 | 7 | 7 | 5 | 0 | 29 | 0 | 3 | 7 | 7 | 7 | 5 | 0 | 29 | 0 | 3 | 7 | 7 | 7 | 5 | 0 | 28 | 0 | 3 | 7 | 7 | 7 | 4 | 0 | 29 | 0 | 3 | 7 | 7 | 7 | 5 | 0 | 29 | 0 | 3 | 7 | 7 | 7 | 5 | 0
Protección | Kits - CARE Package- (meta hogar) | 2400 | 600 | 300 | 0 | 30 | 60 | 75 | 75 | 60 | 0 | 300 | 0 | 30 | 60 | 75 | 75 | 60 | 0 | 1800 | 300 | 0 | 30 | 60 | 75 | 75 | 60 | 0 | 300 | 0 | 30 | 60 | 75 | 75 | 60 | 0 | 300 | 0 | 30 | 60 | 75 | 75 | 60 | 0 | 300 | 0 | 30 | 60 | 75 | 75 | 60 | 0 | 300 | 0 | 30 | 60 | 75 | 75 | 60 | 0 | 300 | 0 | 30 | 60 | 75 | 75 | 60 | 0
Protección | Kits - CARE Package- (meta personas) | 9600 | 2400 | 1200 | 0 | 120 | 240 | 300 | 300 | 240 | 0 | 1200 | 0 | 120 | 240 | 300 | 300 | 240 | 0 | 7200 | 1200 | 0 | 120 | 240 | 300 | 300 | 240 | 0 | 1200 | 0 | 120 | 240 | 300 | 300 | 240 | 0 | 1200 | 0 | 120 | 240 | 300 | 300 | 240 | 0 | 1200 | 0 | 120 | 240 | 300 | 300 | 240 | 0 | 1200 | 0 | 120 | 240 | 300 | 300 | 240 | 0 | 1200 | 0 | 120 | 240 | 300 | 300 | 240 | 0
Protección | Espacios seguros mejorados | 8 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 6 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Protección | Espacios seguros participantes | 5400 | 1800 | 900 | 0 | 0 | 0 | 180 | 360 | 360 | 0 | 900 | 0 | 0 | 0 | 180 | 360 | 360 | 0 | 3600 | 900 | 0 | 0 | 0 | 180 | 360 | 360 | 0 | 900 | 0 | 0 | 0 | 180 | 360 | 360 | 0 | 450 | 0 | 0 | 0 | 90 | 180 | 180 | 0 | 450 | 0 | 0 | 0 | 90 | 180 | 180 | 0 | 450 | 0 | 0 | 0 | 90 | 180 | 180 | 0 | 450 | 0 | 0 | 0 | 90 | 180 | 180 | 0
Salud | Sensibilizaciones salud | 1400 | 1400 | 700 | 0 | 92 | 161 | 161 | 161 | 125 | 0 | 700 | 0 | 92 | 161 | 161 | 161 | 125 | 0
Salud | Servicios salud primaria | 2690 | 2690 | 1345 | 0 | 144 | 300 | 300 | 300 | 301 | 0 | 1345 | 0 | 144 | 300 | 300 | 300 | 301 | 0
Salud | Salud primaria personas únicas | 1345 | 1345 | 673 | 0 | 72 | 150 | 150 | 150 | 151 | 0 | 672 | 0 | 72 | 150 | 150 | 150 | 150 | 0
Salud | Kits post - parto | 140 | 140 | 70 | 0 | 7 | 16 | 16 | 16 | 15 | 0 | 70 | 0 | 7 | 16 | 16 | 16 | 15 | 0
Salud | Atención VBG | 576 | 576 | 288 | 0 | 48 | 60 | 60 | 60 | 60 | 0 | 288 | 0 | 48 | 60 | 60 | 60 | 60 | 0
MPC | Entrega cash multipropósito (meta hogar) | 576 | 576 | 288 | 0 | 30 | 64 | 66 | 64 | 64 | 0 | 288 | 0 | 30 | 64 | 66 | 64 | 64 | 0
MPC | Entrega cash multipropósito (cantidad de entregas x 3) | 1728 | 1728 | 864 | 0 | 90 | 192 | 198 | 192 | 192 | 0 | 864 | 0 | 90 | 192 | 198 | 192 | 192 | 0
4
Metas mensuales
Sector | Actividad | Meta total | May | Jun | Jul | Ago | Sep | Oct | Nov
Protección | Sensibilizaciones general (10%) | 1600 | 0 | 160 | 360 | 360 | 360 | 360 | 0
Protección | Sensibilizaciones VBG (80%) | 6400 | 0 | 640 | 1440 | 1440 | 1440 | 1440 | 0
Protección | Gestión de Casos | 1152 | 0 | 192 | 240 | 240 | 240 | 240 | 0
Protección | Cash VBG | 403 | 0 | 48 | 92 | 92 | 92 | 79 | 0
Protección | Kits - CARE Package- (meta hogar) | 2400 | 0 | 240 | 480 | 600 | 600 | 480 | 0
Protección | Kits - CARE Package- (meta personas) | 9600 | 0 | 960 | 1920 | 2400 | 2400 | 1920 | 0
Protección | Espacios seguros mejorados | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0
Protección | Espacios seguros participantes | 5400 | 0 | 0 | 0 | 1080 | 2160 | 2160 | 0
Salud | Sensibilizaciones salud | 1400 | 0 | 184 | 322 | 322 | 322 | 250 | 0
Salud | Servicios salud primaria | 2690 | 0 | 288 | 600 | 600 | 600 | 602 | 0
Salud | Salud primaria personas únicas | 1345 | 0 | 144 | 300 | 300 | 300 | 301 | 0
Salud | Kits post - parto | 140 | 0 | 14 | 32 | 32 | 32 | 30 | 0
Salud | Atención VBG | 576 | 0 | 96 | 120 | 120 | 120 | 120 | 0
MPC | Entrega cash multipropósito (meta hogar) | 576 | 0 | 60 | 128 | 132 | 128 | 128 | 0
MPC | Entrega cash multipropósito (cantidad de entregas x 3) | 1728 | 0 | 180 | 384 | 396 | 384 | 384 | 0

## Seguimiento Cauca
SEGUIMIENTO MENSUAL - DEPARTAMENTO DE CAUCA
MUNICIPIO: BUENOS AIRES
Sector | Actividad | TOTAL |  |  | May |  |  | Jun |  |  | Jul |  |  | Ago |  |  | Sep |  |  | Oct |  |  | Nov
|  | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av
Protección | Sensibilizaciones general (10%) | 240 | 0 | 0% | 0 |  | 0% | 24 |  | 0% | 54 |  | 0% | 54 |  | 0% | 54 |  | 0% | 54 |  | 0% | 0 |  | 0%
Protección | Sensibilizaciones VBG (80%) | 960 | 0 | 0% | 0 |  | 0% | 96 |  | 0% | 216 |  | 0% | 216 |  | 0% | 216 |  | 0% | 216 |  | 0% | 0 |  | 0%
Protección | Gestión de Casos | 288 | 0 | 0% | 0 |  | 0% | 48 |  | 0% | 60 |  | 0% | 60 |  | 0% | 60 |  | 0% | 60 |  | 0% | 0 |  | 0%
Protección | Cash VBG | 115 | 0 | 0% | 0 |  | 0% | 15 |  | 0% | 25 |  | 0% | 25 |  | 0% | 25 |  | 0% | 25 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta hogar) | 300 | 0 | 0% | 0 |  | 0% | 30 |  | 0% | 60 |  | 0% | 75 |  | 0% | 75 |  | 0% | 60 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta personas) | 1200 | 0 | 0% | 0 |  | 0% | 120 | 0 | 0% | 240 | 0 | 0% | 300 | 0 | 0% | 300 | 0 | 0% | 240 | 0 | 0% |  |  | 0%
Protección | Espacios seguros mejorados | 1 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 1 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0%
Protección | Espacios seguros participantes | 900 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 180 |  | 0% | 360 |  | 0% | 360 |  | 0% | 0 |  | 0%
Salud | Sensibilizaciones | 700 | 0 | 0% | 0 |  | 0% | 92 |  | 0% | 161 |  | 0% | 161 |  | 0% | 161 |  | 0% | 125 |  | 0% | 0 |  | 0%
Salud | Servicios salud primaria | 1345 | 0 | 0% | 0 |  | 0% | 144 |  | 0% | 300 |  | 0% | 300 |  | 0% | 300 |  | 0% | 301 |  | 0% | 0 |  | 0%
Salud | Salud primaria personas únicas | 673 | 0 | 0% | 0 |  | 0% | 72 |  | 0% | 150 |  | 0% | 150 |  | 0% | 150 |  | 0% | 151 |  | 0% | 0 |  | 0%
Salud | Kits post - parto | 70 | 0 | 0% | 0 |  | 0% | 7 |  | 0% | 16 |  | 0% | 16 |  | 0% | 16 |  | 0% | 15 |  | 0% | 0 |  | 0%
Salud | Atención VBG | 288 | 0 | 0% | 0 |  | 0% | 48 |  | 0% | 60 |  | 0% | 60 |  | 0% | 60 |  | 0% | 60 |  | 0% | 0 |  | 0%
MPC | Entrega cash multipropósito (meta hogar) | 288 | 0 | 0% | 0 |  | 0% | 30 |  | 0% | 64 |  | 0% | 66 |  | 0% | 64 |  | 0% | 64 |  | 0% | 0 |  | 0%
MPC | Entrega cash multipropósito (cantidad de entregas x 3) | 864 | 0 | 0% | 0 |  | 0% | 90 |  | 0% | 192 |  | 0% | 198 |  | 0% | 192 |  | 0% | 192 |  | 0% | 0 |  | 0%
MUNICIPIO: MORALES
Sector | Actividad | TOTAL |  |  | May |  |  | Jun |  |  | Jul |  |  | Ago |  |  | Sep |  |  | Oct |  |  | Nov
|  | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av
Protección | Sensibilizaciones general (10%) | 240 | 0 | 0% | 0 |  | 0% | 24 |  | 0% | 54 |  | 0% | 54 |  | 0% | 54 |  | 0% | 54 |  | 0% | 0 |  | 0%
Protección | Sensibilizaciones VBG (80%) | 960 | 0 | 0% | 0 |  | 0% | 96 |  | 0% | 216 |  | 0% | 216 |  | 0% | 216 |  | 0% | 216 |  | 0% | 0 |  | 0%
Protección | Gestión de Casos | 288 | 0 | 0% | 0 |  | 0% | 48 |  | 0% | 60 |  | 0% | 60 |  | 0% | 60 |  | 0% | 60 |  | 0% | 0 |  | 0%
Protección | Cash VBG | 115 | 0 | 0% | 0 |  | 0% | 15 |  | 0% | 25 |  | 0% | 25 |  | 0% | 25 |  | 0% | 25 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta hogar) | 300 | 0 | 0% | 0 |  | 0% | 30 |  | 0% | 60 |  | 0% | 75 |  | 0% | 75 |  | 0% | 60 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta personas) | 1200 | 0 | 0% | 0 |  | 0% | 120 | 0 | 0% | 240 | 0 | 0% | 300 | 0 | 0% | 300 | 0 | 0% | 240 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros mejorados | 1 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 1 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0%
Protección | Espacios seguros participantes | 900 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 180 |  | 0% | 360 |  | 0% | 360 |  | 0% | 0 |  | 0%
Salud | Sensibilizaciones | 700 | 0 | 0% | 0 |  | 0% | 92 |  | 0% | 161 |  | 0% | 161 |  | 0% | 161 |  | 0% | 125 |  | 0% | 0 |  | 0%
Salud | Servicios salud primaria | 1345 | 0 | 0% | 0 |  | 0% | 144 |  | 0% | 300 |  | 0% | 300 |  | 0% | 300 |  | 0% | 301 |  | 0% | 0 |  | 0%
Salud | Salud primaria personas únicas | 672 | 0 | 0% | 0 |  | 0% | 72 |  | 0% | 150 |  | 0% | 150 |  | 0% | 150 |  | 0% | 150 |  | 0% | 0 |  | 0%
Salud | Kits post - parto | 70 | 0 | 0% | 0 |  | 0% | 7 |  | 0% | 16 |  | 0% | 16 |  | 0% | 16 |  | 0% | 15 |  | 0% | 0 |  | 0%
Salud | Atención VBG | 288 | 0 | 0% | 0 |  | 0% | 48 |  | 0% | 60 |  | 0% | 60 |  | 0% | 60 |  | 0% | 60 |  | 0% | 0 |  | 0%
MPC | Entrega cash multipropósito (meta hogar) | 288 | 0 | 0% | 0 |  | 0% | 30 |  | 0% | 64 |  | 0% | 66 |  | 0% | 64 |  | 0% | 64 |  | 0% | 0 |  | 0%
MPC | Entrega cash multipropósito (cantidad de entregas x 3) | 864 | 0 | 0% | 0 |  | 0% | 90 |  | 0% | 192 |  | 0% | 198 |  | 0% | 192 |  | 0% | 192 |  | 0% | 0 |  | 0%
CONSOLIDADO CAUCA
Sector | Actividad | TOTAL |  |  | May |  |  | Jun |  |  | Jul |  |  | Ago |  |  | Sep |  |  | Oct |  |  | Nov
|  | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av
Protección | Sensibilizaciones general (10%) | 480 | 0 | 0% | 0 | 0 | 0% | 48 | 0 | 0% | 108 | 0 | 0% | 108 | 0 | 0% | 108 | 0 | 0% | 108 | 0 | 0% | 0 | 0 | 0%
Protección | Sensibilizaciones VBG (80%) | 1920 | 0 | 0% | 0 | 0 | 0% | 192 | 0 | 0% | 432 | 0 | 0% | 432 | 0 | 0% | 432 | 0 | 0% | 432 | 0 | 0% | 0 | 0 | 0%
Protección | Gestión de Casos | 576 | 0 | 0% | 0 | 0 | 0% | 96 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 0 | 0 | 0%
Protección | Cash VBG | 230 | 0 | 0% | 0 | 0 | 0% | 30 | 0 | 0% | 50 | 0 | 0% | 50 | 0 | 0% | 50 | 0 | 0% | 50 | 0 | 0% | 0 | 0 | 0%
Protección | Kits - CARE Package- (meta hogar) | 600 | 0 | 0% | 0 | 0 | 0% | 60 | 0 | 0% | 120 | 0 | 0% | 150 | 0 | 0% | 150 | 0 | 0% | 120 | 0 | 0% | 0 | 0 | 0%
Protección | Kits - CARE Package- (meta personas) | 2400 | 0 | 0% | 0 | 0 | 0% | 240 | 0 | 0% | 480 | 0 | 0% | 600 | 0 | 0% | 600 | 0 | 0% | 480 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros mejorados | 2 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 2 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros participantes | 1800 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 360 | 0 | 0% | 720 | 0 | 0% | 720 | 0 | 0% | 0 | 0 | 0%
Salud | Sensibilizaciones | 1400 | 0 | 0% | 0 | 0 | 0% | 184 | 0 | 0% | 322 | 0 | 0% | 322 | 0 | 0% | 322 | 0 | 0% | 250 | 0 | 0% | 0 | 0 | 0%
Salud | Servicios salud primaria | 2690 | 0 | 0% | 0 | 0 | 0% | 288 | 0 | 0% | 600 | 0 | 0% | 600 | 0 | 0% | 600 | 0 | 0% | 602 | 0 | 0% | 0 | 0 | 0%
Salud | Salud primaria personas únicas | 1345 | 0 | 0% | 0 | 0 | 0% | 144 | 0 | 0% | 300 | 0 | 0% | 300 | 0 | 0% | 300 | 0 | 0% | 301 | 0 | 0% | 0 | 0 | 0%
Salud | Kits post - parto | 140 | 0 | 0% | 0 | 0 | 0% | 14 | 0 | 0% | 32 | 0 | 0% | 32 | 0 | 0% | 32 | 0 | 0% | 30 | 0 | 0% | 0 | 0 | 0%
Salud | Atención VBG | 576 | 0 | 0% | 0 | 0 | 0% | 96 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 0 | 0 | 0%
MPC | Entrega cash multipropósito (meta hogar) | 576 | 0 | 0% | 0 | 0 | 0% | 60 | 0 | 0% | 128 | 0 | 0% | 132 | 0 | 0% | 128 | 0 | 0% | 128 | 0 | 0% | 0 | 0 | 0%
MPC | Entrega cash multipropósito (cantidad de entregas x 3) | 1728 | 0 | 0% | 0 | 0 | 0% | 180 | 0 | 0% | 384 | 0 | 0% | 396 | 0 | 0% | 384 | 0 | 0% | 384 | 0 | 0% | 0 | 0 | 0%

## Seguimiento NdS
SEGUIMIENTO MENSUAL - DEPARTAMENTO DE NORTE DE SANTANDER
MUNICIPIO: ABREGO
Sector | Actividad | TOTAL |  |  | May |  |  | Jun |  |  | Jul |  |  | Ago |  |  | Sep |  |  | Oct |  |  | Nov
|  | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av
Protección | Sensibilizaciones general (10%) | 240 | 0 | 0% | 0 |  | 0% | 24 |  | 0% | 54 |  | 0% | 54 |  | 0% | 54 |  | 0% | 54 |  | 0% | 0 |  | 0%
Protección | Sensibilizaciones VBG (80%) | 960 | 0 | 0% | 0 |  | 0% | 96 |  | 0% | 216 |  | 0% | 216 |  | 0% | 216 |  | 0% | 216 |  | 0% | 0 |  | 0%
Protección | Gestión de Casos | 96 | 0 | 0% | 0 |  | 0% | 16 |  | 0% | 20 |  | 0% | 20 |  | 0% | 20 |  | 0% | 20 |  | 0% | 0 |  | 0%
Protección | Cash VBG | 29 | 0 | 0% | 0 |  | 0% | 3 |  | 0% | 7 |  | 0% | 7 |  | 0% | 7 |  | 0% | 5 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta hogar) | 300 | 0 | 0% | 0 |  | 0% | 30 |  | 0% | 60 |  | 0% | 75 |  | 0% | 75 |  | 0% | 60 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta personas) | 1200 | 0 | 0% | 0 |  | 0% | 120 | 0 | 0% | 240 | 0 | 0% | 300 | 0 | 0% | 300 | 0 | 0% | 240 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros mejorados | 1 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 1 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0%
Protección | Espacios seguros participantes | 900 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 180 |  | 0% | 360 |  | 0% | 360 |  | 0% | 0 |  | 0%
MUNICIPIO: OCAÑA
Sector | Actividad | TOTAL |  |  | May |  |  | Jun |  |  | Jul |  |  | Ago |  |  | Sep |  |  | Oct |  |  | Nov
|  | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av
Protección | Sensibilizaciones general (10%) | 240 | 0 | 0% | 0 |  | 0% | 24 |  | 0% | 54 |  | 0% | 54 |  | 0% | 54 |  | 0% | 54 |  | 0% | 0 |  | 0%
Protección | Sensibilizaciones VBG (80%) | 960 | 0 | 0% | 0 |  | 0% | 96 |  | 0% | 216 |  | 0% | 216 |  | 0% | 216 |  | 0% | 216 |  | 0% | 0 |  | 0%
Protección | Gestión de Casos | 96 | 0 | 0% | 0 |  | 0% | 16 |  | 0% | 20 |  | 0% | 20 |  | 0% | 20 |  | 0% | 20 |  | 0% | 0 |  | 0%
Protección | Cash VBG | 29 | 0 | 0% | 0 |  | 0% | 3 |  | 0% | 7 |  | 0% | 7 |  | 0% | 7 |  | 0% | 5 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta hogar) | 300 | 0 | 0% | 0 |  | 0% | 30 |  | 0% | 60 |  | 0% | 75 |  | 0% | 75 |  | 0% | 60 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta personas) | 1200 | 0 | 0% | 0 |  | 0% | 120 | 0 | 0% | 240 | 0 | 0% | 300 | 0 | 0% | 300 | 0 | 0% | 240 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros mejorados | 1 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 1 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0%
Protección | Espacios seguros participantes | 900 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 180 |  | 0% | 360 |  | 0% | 360 |  | 0% | 0 |  | 0%
MUNICIPIO: CONVENCIÓN
Sector | Actividad | TOTAL |  |  | May |  |  | Jun |  |  | Jul |  |  | Ago |  |  | Sep |  |  | Oct |  |  | Nov
|  | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av
Protección | Sensibilizaciones general (10%) | 160 | 0 | 0% | 0 |  | 0% | 16 |  | 0% | 36 |  | 0% | 36 |  | 0% | 36 |  | 0% | 36 |  | 0% | 0 |  | 0%
Protección | Sensibilizaciones VBG (80%) | 640 | 0 | 0% | 0 |  | 0% | 64 |  | 0% | 144 |  | 0% | 144 |  | 0% | 144 |  | 0% | 144 |  | 0% | 0 |  | 0%
Protección | Gestión de Casos | 96 | 0 | 0% | 0 |  | 0% | 16 |  | 0% | 20 |  | 0% | 20 |  | 0% | 20 |  | 0% | 20 |  | 0% | 0 |  | 0%
Protección | Cash VBG | 29 | 0 | 0% | 0 |  | 0% | 3 |  | 0% | 7 |  | 0% | 7 |  | 0% | 7 |  | 0% | 5 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta hogar) | 300 | 0 | 0% | 0 |  | 0% | 30 |  | 0% | 60 |  | 0% | 75 |  | 0% | 75 |  | 0% | 60 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta personas) | 1200 | 0 | 0% | 0 |  | 0% | 120 | 0 | 0% | 240 | 0 | 0% | 300 | 0 | 0% | 300 | 0 | 0% | 240 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros mejorados | 1 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 1 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0%
Protección | Espacios seguros participantes | 450 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 90 |  | 0% | 180 |  | 0% | 180 |  | 0% | 0 |  | 0%
MUNICIPIO: TEORAMA
Sector | Actividad | TOTAL |  |  | May |  |  | Jun |  |  | Jul |  |  | Ago |  |  | Sep |  |  | Oct |  |  | Nov
|  | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av
Protección | Sensibilizaciones general (10%) | 160 | 0 | 0% | 0 |  | 0% | 16 |  | 0% | 36 |  | 0% | 36 |  | 0% | 36 |  | 0% | 36 |  | 0% | 0 |  | 0%
Protección | Sensibilizaciones VBG (80%) | 640 | 0 | 0% | 0 |  | 0% | 64 |  | 0% | 144 |  | 0% | 144 |  | 0% | 144 |  | 0% | 144 |  | 0% | 0 |  | 0%
Protección | Gestión de Casos | 96 | 0 | 0% | 0 |  | 0% | 16 |  | 0% | 20 |  | 0% | 20 |  | 0% | 20 |  | 0% | 20 |  | 0% | 0 |  | 0%
Protección | Cash VBG | 28 | 0 | 0% | 0 |  | 0% | 3 |  | 0% | 7 |  | 0% | 7 |  | 0% | 7 |  | 0% | 4 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta hogar) | 300 | 0 | 0% | 0 |  | 0% | 30 |  | 0% | 60 |  | 0% | 75 |  | 0% | 75 |  | 0% | 60 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta personas) | 1200 | 0 | 0% | 0 |  | 0% | 120 | 0 | 0% | 240 | 0 | 0% | 300 | 0 | 0% | 300 | 0 | 0% | 240 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros mejorados | 1 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 1 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0%
Protección | Espacios seguros participantes | 450 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 90 |  | 0% | 180 |  | 0% | 180 |  | 0% | 0 |  | 0%
MUNICIPIO: HACARÍ
Sector | Actividad | TOTAL |  |  | May |  |  | Jun |  |  | Jul |  |  | Ago |  |  | Sep |  |  | Oct |  |  | Nov
|  | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av
Protección | Sensibilizaciones general (10%) | 160 | 0 | 0% | 0 |  | 0% | 16 |  | 0% | 36 |  | 0% | 36 |  | 0% | 36 |  | 0% | 36 |  | 0% | 0 |  | 0%
Protección | Sensibilizaciones VBG (80%) | 640 | 0 | 0% | 0 |  | 0% | 64 |  | 0% | 144 |  | 0% | 144 |  | 0% | 144 |  | 0% | 144 |  | 0% | 0 |  | 0%
Protección | Gestión de Casos | 96 | 0 | 0% | 0 |  | 0% | 16 |  | 0% | 20 |  | 0% | 20 |  | 0% | 20 |  | 0% | 20 |  | 0% | 0 |  | 0%
Protección | Cash VBG | 29 | 0 | 0% | 0 |  | 0% | 3 |  | 0% | 7 |  | 0% | 7 |  | 0% | 7 |  | 0% | 5 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta hogar) | 300 | 0 | 0% | 0 |  | 0% | 30 |  | 0% | 60 |  | 0% | 75 |  | 0% | 75 |  | 0% | 60 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta personas) | 1200 | 0 | 0% | 0 |  | 0% | 120 | 0 | 0% | 240 | 0 | 0% | 300 | 0 | 0% | 300 | 0 | 0% | 240 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros mejorados | 1 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 1 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0%
Protección | Espacios seguros participantes | 450 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 90 |  | 0% | 180 |  | 0% | 180 |  | 0% | 0 |  | 0%
MUNICIPIO: LA PLAYA DE BELÉN
Sector | Actividad | TOTAL |  |  | May |  |  | Jun |  |  | Jul |  |  | Ago |  |  | Sep |  |  | Oct |  |  | Nov
|  | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av
Protección | Sensibilizaciones general (10%) | 160 | 0 | 0% | 0 |  | 0% | 16 |  | 0% | 36 |  | 0% | 36 |  | 0% | 36 |  | 0% | 36 |  | 0% | 0 |  | 0%
Protección | Sensibilizaciones VBG (80%) | 640 | 0 | 0% | 0 |  | 0% | 64 |  | 0% | 144 |  | 0% | 144 |  | 0% | 144 |  | 0% | 144 |  | 0% | 0 |  | 0%
Protección | Gestión de Casos | 96 | 0 | 0% | 0 |  | 0% | 16 |  | 0% | 20 |  | 0% | 20 |  | 0% | 20 |  | 0% | 20 |  | 0% | 0 |  | 0%
Protección | Cash VBG | 29 | 0 | 0% | 0 |  | 0% | 3 |  | 0% | 7 |  | 0% | 7 |  | 0% | 7 |  | 0% | 5 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta hogar) | 300 | 0 | 0% | 0 |  | 0% | 30 |  | 0% | 60 |  | 0% | 75 |  | 0% | 75 |  | 0% | 60 |  | 0% | 0 |  | 0%
Protección | Kits - CARE Package- (meta personas) | 1200 | 0 | 0% | 0 |  | 0% | 120 | 0 | 0% | 240 | 0 | 0% | 300 | 0 | 0% | 300 | 0 | 0% | 240 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros mejorados | 1 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 1 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0%
Protección | Espacios seguros participantes | 450 | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 90 |  | 0% | 180 |  | 0% | 180 |  | 0% | 0 |  | 0%
CONSOLIDADO NORTE DE SANTANDER
Sector | Actividad | TOTAL |  |  | May |  |  | Jun |  |  | Jul |  |  | Ago |  |  | Sep |  |  | Oct |  |  | Nov
|  | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av | Meta | Avance | % Av
Protección | Sensibilizaciones general (10%) | 1120 | 0 | 0% | 0 | 0 | 0% | 112 | 0 | 0% | 252 | 0 | 0% | 252 | 0 | 0% | 252 | 0 | 0% | 252 | 0 | 0% | 0 | 0 | 0%
Protección | Sensibilizaciones VBG (80%) | 4480 | 0 | 0% | 0 | 0 | 0% | 448 | 0 | 0% | 1008 | 0 | 0% | 1008 | 0 | 0% | 1008 | 0 | 0% | 1008 | 0 | 0% | 0 | 0 | 0%
Protección | Gestión de Casos | 576 | 0 | 0% | 0 | 0 | 0% | 96 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 0 | 0 | 0%
Protección | Cash VBG | 173 | 0 | 0% | 0 | 0 | 0% | 18 | 0 | 0% | 42 | 0 | 0% | 42 | 0 | 0% | 42 | 0 | 0% | 29 | 0 | 0% | 0 | 0 | 0%
Protección | Kits - CARE Package- (meta hogar) | 1800 | 0 | 0% | 0 | 0 | 0% | 180 | 0 | 0% | 360 | 0 | 0% | 450 | 0 | 0% | 450 | 0 | 0% | 360 | 0 | 0% | 0 | 0 | 0%
Protección | Kits - CARE Package- (meta personas) | 7200 | 0 | 0% | 0 | 0 | 0% | 720 | 0 | 0% | 1440 | 0 | 0% | 1800 | 0 | 0% | 1800 | 0 | 0% | 1440 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros mejorados | 6 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 6 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros participantes | 3600 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 720 | 0 | 0% | 1440 | 0 | 0% | 1440 | 0 | 0% | 0 | 0 | 0%

## Consolidado
CONSOLIDADO POR DEPARTAMENTO Y GLOBAL - PROYECTO CONESPERANZA
Sector | Actividad | CAUCA - Meta | CAUCA - Avance | CAUCA - % Av | NORTE DE SANTANDER - Meta | NORTE DE SANTANDER - Avance | NORTE DE SANTANDER - % Av | GLOBAL - Meta | GLOBAL - Avance | GLOBAL - % Av
Protección | Sensibilizaciones Gen | 480 | 0 | 0% | 1120 | 0 | 0% | 1600 | 0 | 0%
Protección | Sensibilizaciones VBG | 1920 | 0 | 0% | 4480 | 0 | 0% | 6400 | 0 | 0%
Protección | Gestión de Casos | 576 | 0 | 0% | 576 | 0 | 0% | 1152 | 0 | 0%
Protección | Cash VBG | 230 | 0 | 0% | 173 | 0 | 0% | 403 | 0 | 0%
Protección | Kits - CARE Package- (meta hogar) | 600 | 0 | 0% | 1800 | 0 | 0% | 2400 | 0 | 0%
Protección | Kits - CARE Package- (meta personas) | 2400 | 0 | 0% | 7200 | 0 | 0% | 9600 | 0 | 0%
Protección | Espacios seguros | 2 | 0 | 0% | 6 | 0 | 0% | 8 | 0 | 0%
Protección | Espacios seguros- participantes | 1800 | 0 | 0% | 3600 | 0 | 0% | 5400 | 0 | 0%
Salud | Sensibilizaciones salud | 1400 | 0 | 0% | 0 | 0 | 0% | 1400 | 0 | 0%
Salud | Salud - servicios | 2690 | 0 | 0% | 0 | 0 | 0% | 2690 | 0 | 0%
Salud | Salud - personas | 1345 | 0 | 0% | 0 | 0 | 0% | 1345 | 0 | 0%
Salud | Kits post - parto | 140 | 0 | 0% | 0 | 0 | 0% | 140 | 0 | 0%
Salud | Atención VBG | 576 | 0 | 0% | 0 | 0 | 0% | 576 | 0 | 0%
MPC | MPCA hogar | 576 | 0 | 0% | 0 | 0 | 0% | 576 | 0 | 0%
MPC | MPCA personas | 1728 | 0 | 0% | 0 | 0 | 0% | 1728 | 0 | 0%
CONSOLIDADO AVANCE MENSUAL METAS
Sector | Actividad | May Meta | May Avance | % Av | Jun Meta | Jun Avance | % Av | Jul Meta | Jul Avance | % Av | Ago Meta | Ago Avance | % Av | Sep Meta | Sep Avance | % Av | Oct Meta | Oct Avance | % Av | Nov Meta | Nov Avance | % Av
Protección | Sensibilizaciones Gen | 0 | 0 | 0% | 160 | 0 | 0% | 360 | 0 | 0% | 360 | 0 | 0% | 360 | 0 | 0% | 360 | 0 | 0% | 0 | 0 | 0%
Protección | Sensibilizaciones VBG | 0 | 0 | 0% | 640 | 0 | 0% | 1440 | 0 | 0% | 1440 | 0 | 0% | 1440 | 0 | 0% | 1440 | 0 | 0% | 0 | 0 | 0%
Protección | Gestión de Casos | 0 | 0 | 0% | 192 | 0 | 0% | 240 | 0 | 0% | 240 | 0 | 0% | 240 | 0 | 0% | 240 | 0 | 0% | 0 | 0 | 0%
Protección | Cash VBG | 0 | 0 | 0% | 48 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 79 | 0 | 0% | 0 | 0 | 0%
Protección | Kits - CARE Package- (meta hogar) | 0 | 0 | 0% | 240 | 0 | 0% | 480 | 0 | 0% | 600 | 0 | 0% | 600 | 0 | 0% | 480 | 0 | 0% | 0 | 0 | 0%
Protección | Kits - CARE Package- (meta personas) | 0 | 0 | 0% | 960 | 0 | 0% | 1920 | 0 | 0% | 2400 | 0 | 0% | 2400 | 0 | 0% | 1920 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 8 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0%
Protección | Espacios seguros- participantes | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 1080 | 0 | 0% | 2160 | 0 | 0% | 2160 | 0 | 0% | 0 | 0 | 0%
Salud | Sensibilizaciones salud | 0 | 0 | 0% | 184 | 0 | 0% | 322 | 0 | 0% | 322 | 0 | 0% | 322 | 0 | 0% | 250 | 0 | 0% | 0 | 0 | 0%
Salud | Salud - servicios | 0 | 0 | 0% | 288 | 0 | 0% | 600 | 0 | 0% | 600 | 0 | 0% | 600 | 0 | 0% | 602 | 0 | 0% | 0 | 0 | 0%
Salud | Salud - personas | 0 | 0 | 0% | 144 | 0 | 0% | 300 | 0 | 0% | 300 | 0 | 0% | 300 | 0 | 0% | 301 | 0 | 0% | 0 | 0 | 0%
Salud | Kits post - parto | 0 | 0 | 0% | 14 | 0 | 0% | 32 | 0 | 0% | 32 | 0 | 0% | 32 | 0 | 0% | 30 | 0 | 0% | 0 | 0 | 0%
Salud | Atención VBG | 0 | 0 | 0% | 96 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 0 | 0 | 0%
MPC | MPCA hogar | 0 | 0 | 0% | 60 | 0 | 0% | 128 | 0 | 0% | 132 | 0 | 0% | 128 | 0 | 0% | 128 | 0 | 0% | 0 | 0 | 0%
MPC | MPCA personas | 0 | 0 | 0% | 180 | 0 | 0% | 384 | 0 | 0% | 396 | 0 | 0% | 384 | 0 | 0% | 384 | 0 | 0% | 0 | 0 | 0%

## Indicator Targets
[8 empty] | May |  |  | June |  |  | July |  |  | August |  |  | September |  |  | October |  |  | November
Sector | No. | Indicator Title | Actividad (es) asociadas | Target (individuals) | Target (Household) | Target (consultations) | Total value of cash transferred | Monthly target | Cummulative (LOP) | % Cummulative (LOP) | Monthly target | Cummulative (LOP) | % Cummulative (LOP) | Monthly target | Cummulative (LOP) | % Cummulative (LOP) | Monthly target | Cummulative (LOP) | % Cummulative (LOP) | Monthly target | Cummulative (LOP) | % Cummulative (LOP) | Monthly target | Cummulative (LOP) | % Cummulative (LOP) | Monthly target | Cummulative (LOP) | % Cummulative (LOP)
MPCA | C-CA1 -MPC.a: | Number of households having received Multi-Purpose Cash (MPC) | Entrega MPCA | 2016 | 576 |  |  | 0 | 0 | 0% | 60 | 0 | 0% | 128 | 0 | 0% | 132 | 0 | 0% | 128 | 0 | 0% | 128 | 0 | 0% | 0 | 0 | #DIV/0! | 576
MPCA | CUST-03-C: | Total value of Sector specific unconditional cash transfers distributed in USD | Entrega MPCA |  |  |  |  | 0 | 0 | 0%
Health | C-CA1-H.8: | Number of primary healthcare consultations provided | Servicios Salud Primaria | 1345 |  | 2690 |  | 0 | 0 | 0% | 288 | 0 | 0% | 600 | 0 | 0% | 600 | 0 | 0% | 600 | 0 | 0% | 602 | 0 | 0% | 0 | 0 | #DIV/0! | 2690
Health | C-CA11-SP.5: | Number of violence survivors receiving medical assistance, including clinical management of rape | Atención VBG | 576 |  |  |  | 0 | 0 | 0% | 96 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 120 | 0 | 0% | 0 | 0 | #DIV/0! | 576
Protection | C-CA9-CP.3 | Number of children receiving protection support (e.g. family tracing, reunification, reintegration, case management services, etc) | [5 empty] | 0 | 0 | 0%
Protection | C-CA9-CP.4: | Number of people accessing protection activities and/or services through child-friendly spaces | [5 empty] | 0 | 0 | 0%
Protection | C-CA11-PS.2: | Number of people receiving violence psycho-social support and/or violence case management (for medical support, use SP.5) | Gestiones de caso VBG y espacios seguros | 6552 |  |  |  | 0 | 0 | 0% | 192 | 0 | 0% | 240 | 0 | 0% | 1320 | 0 | 0% | 2400 | 0 | 0% | 2400 | 0 | 0% | 0 | 0 | #DIV/0! | 6552
Protection | C-CA16 - PP.b: | Number of people affected benefiting from emergency cash assistance or direct service payments | CASH VBG | 403 |  |  |  | 0 | 0 | 0% | 48 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 92 | 0 | 0% | 79 | 0 | 0% | 0 | 0 | #DIV/0! | 403
Protection | CUST-02-P: | Total value of Sector specific unconditional cash transfers distributed in USD | CASH VBG |  |  |  |  | 0 | 0 | 0%
GVB Protection | C-CA19 - PS.a: | Number of individuals who received life‑saving protection support through newly established or strengthened violence prevention and risk‑mitigation mechanisms. | Sensibilizaciones y entrega de CARE Package | 17600 | 2400 |  |  | 0 | 0 | 0% | 1760 | 0 | 0% | 3720 | 0 | 0% | 4200 | 0 | 0% | 4200 | 0 | 0% | 3720 | 0 | 0% | 0 | 0 | #DIV/0! | 17600
Nutrition | C-CA3-N.4: | Number of people screened for acute malnutrition
Nutrition | C-CA4-N.6: | Number of people benefitting training and/or community awareness sessions on infant and young child feeding in emergencies
Nutrition | C-CA5-N.a: | Number of households with malnourished children received cash and voucher assistance
Nutrition | CUST-01-N: | Total value of Sectorspecific unconditional cash transfers distributed in USD
WASH | C-CA6-WS.6: | Number of people accessing sufficient and safe water for drinking, cooking and/or personal hygiene use as per agreed sector standard
WASH | C-CA7-WS.c: | Number of households receiving hygiene kits (incl. menstrual hygiene items)
WASH | C-CA8-WS.17: | Number of people receiving WASH/hygiene messaging
AAP | AAP: | Percentage of issues identified in feedback processes for which solutions are in process or closed | [5 empty] | 0 | 0 | 0%

## Dashboard
DASHBOARD DE AVANCE - PROYECTO CONESPERANZA